## Realpage Project Plan 2020
% Complete | Task Name | Duration | Start | Finish | Predecessors | Assigned To | Status | Comments
83% | Realpage Implementation | 392d | 2019-08-26 | 2021-02-23 |  | Ade Ayeni | In Progress
100% | Vitae Residences (Onesite to Onesite Timetable) | 122d | 2019-08-26 | 2020-02-11 |  | Ade Ayeni | Complete
100% | Termination Letter Received by CA (Asset Closed 8/29/19) | 1d | 2019-08-26 | 2019-08-26 |  |  | Complete
100% | Accounting setup | 4d | 2019-08-26 | 2019-08-29 | 3SS |  | Complete
100% | Send Accounting RealPage Order Number for Site | 4d | 2019-08-26 | 2019-08-29 |  |  | Complete
100% | Set up RealPage Accounting/Spend Management | 1d | 2019-08-29 | 2019-08-29 | 5FF |  | Complete
100% | Leasing and Rents (Consulting & Standard Business Model) | 13d | 2019-08-27 | 2019-09-12 | 4SS |  | Complete
100% | Conversion/Go Live | 7d | 2019-08-27 | 2019-09-04 |  |  | Complete
100% | Onesite to Onesite Migration | 7d | 2019-08-27 | 2019-09-04 | 3 |  | Complete
100% | Post Migration | 6d | 2019-09-05 | 2019-09-12 |  |  | Complete
100% | Add Additional Fiscal Years in Onesite | 1d | 2019-09-05 | 2019-09-05 | 9 | Ade Ayeni | Complete
100% | Confirm Delinquent/Prepaid Amounts Match Cut-off Date Data | 3d | 2019-09-06 | 2019-09-10 | 11 |  | Complete
100% | Confirm Transactions Match Cut-off Date Data | 3d | 2019-09-06 | 2019-09-10 | 12SS |  | Complete
100% | Begin Data Entry for Manual Data | 6d | 2019-09-05 | 2019-09-12 | 9 |  | Complete
100% | Resident Portal | 1d | 2019-09-04 | 2019-09-04 | 8FF |  | Complete
100% | Payments | 8d | 2019-08-28 | 2019-09-06 |  |  | Complete
100% | Information for Payments | 6d | 2019-08-28 | 2019-09-04 |  |  | Complete
100% | Retrieve Voided Check/Bank Letter Verification | 3d | 2019-08-28 | 2019-08-30 | 3FS +1d |  | Complete
100% | Retrieve Average Transaction Amount | 3d | 2019-08-28 | 2019-08-30 | 3FS +1d |  | Complete
100% | Retrieve Highest Rent Amount | 3d | 2019-08-28 | 2019-08-30 | 3FS +1d |  | Complete
100% | Retrieve W9 | 3d | 2019-08-28 | 2019-08-30 | 3FS +1d |  | Complete
100% | Send Documents/Information to Payments Consultant | 3d | 2019-09-02 | 2019-09-04 | 18, 19, 20, 21 |  | Complete
100% | Go Live | 1d | 2019-09-06 | 2019-09-06 | 8FS +1d |  | Complete
100% | Resident Direct | 1d | 2019-09-06 | 2019-09-06 | 8FS +1d |  | Complete
100% | Facilities | 1d | 2019-09-05 | 2019-09-05 | 9 |  | Complete
100% | Document Management (product) | 16d | 2020-01-21 | 2020-02-11 |  |  | Complete
100% | Blue Moon | 12d | 2020-01-21 | 2020-02-05 |  |  | Complete | Delayed obtaining Blue Moon credentials
100% | Obtain Blue Moon Credentials | 1d | 2020-01-21 | 2020-01-21 | 3FS +105d |  | Complete
100% | Update OneSite with Credentials | 0 | 2020-01-21 | 2020-01-21 | 28 | Ade Ayeni | Complete
100% | Confirm Blue Moon Connection | 1d | 2020-01-27 | 2020-01-27 | 29FS +3d |  | Complete
100% | Confirm Blue Moon Docs to be used | 1d | 2020-02-05 | 2020-02-05 | 30FS +6d |  | Complete
100% | Go Live | 4d | 2020-02-06 | 2020-02-11 | 31 |  | Complete
100% | Consulting for Blue Moon Packets | 4d | 2020-02-06 | 2020-02-11 |  |  | Complete
100% | Test Packet Ready for Review | 4d | 2020-02-06 | 2020-02-11 |  |  | Complete
100% | Discuss anything not populating or generating correctly on custom forms | 4d | 2020-02-06 | 2020-02-11 | 31 |  | Complete
100% | Update any Leasing & Rents changes and merge fields, if necessary | 4d | 2020-02-06 | 2020-02-11 | 35SS |  | Complete
100% | Review and Confirm Packet Content | 4d | 2020-02-06 | 2020-02-11 | 35SS |  | Complete
100% | Screening | 0 | 2019-09-05 | 2019-09-05 | 9FF +1d |  | Complete
100% | Online Leasing | 3d | 2019-09-05 | 2019-09-09 |  |  | Complete
100% | Online Leasing Goes Live | 1d | 2019-09-05 | 2019-09-05 | 9FF +1d |  | Complete
100% | Website Link Sent to Site Management to update current Website | 1d | 2019-09-05 | 2019-09-05 | 40FF | Ade Ayeni | Complete
100% | Site Management Completion/Update | 2d | 2019-09-06 | 2019-09-09 | 41 |  | Complete
100% | eSupply GPO | 1d | 2019-09-05 | 2019-09-05 | 8 |  | Complete
100% | eProcurement | 6d | 2019-09-05 | 2019-09-12 |  |  | Complete
100% | Vendors Set up | 5d | 2019-09-05 | 2019-09-11 | 8 |  | Complete
100% | eProcurment completion | 1d | 2019-09-12 | 2019-09-12 | 45 |  | Complete
100% | Vendor Compliance | 1d | 2019-09-11 | 2019-09-11 | 45FF |  | Complete
100% | Syndication | 14d | 2019-08-28 | 2019-09-16 |  |  | Complete
100% | Questionnaire Sent to Marketing | 1d | 2019-08-28 | 2019-08-28 | 3FS +1d |  | Complete
100% | Questionnaire Completed | 13d | 2019-08-29 | 2019-09-16 | 49 |  | Complete
100% | Answer Automation (Call Center) | 5d | 2019-10-17 | 2019-10-23 |  |  | Complete
100% | Questionnaire Sent to Operations | 1d | 2019-10-17 | 2019-10-17 |  |  | Complete
100% | Questionnaire Completed | 1d | 2019-10-23 | 2019-10-23 | 52FS +3d |  | Complete
100% | Vitae Residences Completed | 1d | 2019-09-12 | 2019-09-12 | 44FF |  | Complete
100% | Luther Towers (Onesite to Onesite Timetable) | 113d | 2019-10-17 | 2020-03-23 |  | Ade Ayeni | Complete
100% | Asset Closed | 1d | 2020-02-28 | 2020-02-28 |  |  | Complete
100% | RealPage Questionnaire | 1d | 2020-03-02 | 2020-03-02 | 56 |  | Complete
100% | Accounting setup | 4d | 2020-02-28 | 2020-03-04 | 56SS |  | Complete
100% | Send Accounting RealPage Order Number for Site | 4d | 2020-02-28 | 2020-03-04 |  |  | Complete
100% | Set up RealPage Accounting/Spend Management | 1d | 2020-03-04 | 2020-03-04 | 59FF |  | Complete
100% | Leasing and Rents (Consulting & Standard Business Model) | 13d | 2020-03-02 | 2020-03-18 | 58SS |  | Complete
100% | Conversion/Go Live | 7d | 2020-03-02 | 2020-03-10 |  |  | Complete
100% | Onesite to Onesite Migration | 7d | 2020-03-02 | 2020-03-10 | 56 |  | Complete
100% | Post Migration | 6d | 2020-03-11 | 2020-03-18 |  |  | Complete
100% | Add Additional Fiscal Years in Onesite | 1d | 2020-03-11 | 2020-03-11 | 63 | Ade Ayeni | Complete
100% | Confirm Delinquent/Prepaid Amounts Match Cut-off Date Data | 3d | 2020-03-12 | 2020-03-16 | 65 |  | Complete
100% | Confirm Transactions Match Cut-off Date Data | 3d | 2020-03-12 | 2020-03-16 | 66SS |  | Complete
100% | Begin Data Entry for Manual Data | 6d | 2020-03-11 | 2020-03-18 | 63 |  | Complete
100% | Resident Portal | 1d | 2020-03-10 | 2020-03-10 | 62FF |  | Complete
100% | Payments | 13d | 2020-03-03 | 2020-03-19 |  |  | Complete
100% | Information for Payments | 3d | 2020-03-03 | 2020-03-05 |  |  | Complete
100% | Retrieve Voided Check/Bank Letter Verification | 3d | 2020-03-03 | 2020-03-05 | 56FS +1d |  | Complete
100% | Retrieve Average Transaction Amount | 3d | 2020-03-03 | 2020-03-05 | 56FS +1d |  | Complete
100% | Retrieve Highest Rent Amount | 3d | 2020-03-03 | 2020-03-05 | 56FS +1d |  | Complete
100% | Retrieve W9 | 3d | 2020-03-03 | 2020-03-05 | 56FS +1d |  | Complete
100% | Send Documents/Information to Payments Consultant | 0 | 2020-03-05 | 2020-03-05 | 72, 73, 74, 75 |  | Complete
100% | Go Live | 10d | 2020-03-06 | 2020-03-19 | 76 |  | Complete
100% | Resident Direct | 1d | 2020-03-19 | 2020-03-19 | 77FF |  | Complete
100% | Facilities |  | 2020-03-11 |  | 63 |  | Complete
100% | Document Management (product) | 16d | 2020-03-02 | 2020-03-23 |  |  | Complete
100% | Blue Moon | 12d | 2020-03-02 | 2020-03-17 |  |  | Complete | Delayed obtaining Blue Moon credentials
100% | Obtain Blue Moon Credentials | 1d | 2020-03-02 | 2020-03-02 | 56 |  | Complete
100% | Update OneSite with Credentials | 0 | 2020-03-02 | 2020-03-02 | 82 | Ade Ayeni | Complete
100% | Confirm Blue Moon Connection | 1d | 2020-03-06 | 2020-03-06 | 83FS +3d |  | Complete
100% | Confirm Blue Moon Docs to be used | 1d | 2020-03-17 | 2020-03-17 | 84FS +6d |  | Complete
100% | Go Live | 4d | 2020-03-18 | 2020-03-23 | 85 |  | Complete
100% | Consulting for Blue Moon Packets | 4d | 2020-03-18 | 2020-03-23 |  |  | Complete
100% | Test Packet Ready for Review | 4d | 2020-03-18 | 2020-03-23 |  |  | Complete
100% | Discuss anything not populating or generating correctly on custom forms | 4d | 2020-03-18 | 2020-03-23 | 85 |  | Complete
100% | Update any Leasing & Rents changes and merge fields, if necessary | 4d | 2020-03-18 | 2020-03-23 | 89SS |  | Complete
100% | Review and Confirm Packet Content | 4d | 2020-03-18 | 2020-03-23 | 89SS |  | Complete
100% | Screening | 0 | 2020-03-11 | 2020-03-11 | 63FF +1d |  | Complete
100% | Online Leasing | 3d | 2020-03-11 | 2020-03-13 |  |  | Complete
100% | Online Leasing Goes Live | 1d | 2020-03-11 | 2020-03-11 | 63FF +1d |  | Complete
100% | Website Link Sent to Site Management to update current Website | 1d | 2020-03-11 | 2020-03-11 | 94FF | Ade Ayeni | Complete
100% | Site Management Completion/Update | 2d | 2020-03-12 | 2020-03-13 | 95 |  | Complete
100% | eSupply GPO | 1d | 2020-03-11 | 2020-03-11 | 62 |  | Complete
100% | eProcurement | 6d | 2020-03-11 | 2020-03-18 |  |  | Complete
100% | Vendors Set up | 5d | 2020-03-11 | 2020-03-17 | 62 |  | Complete
100% | eProcurment completion | 1d | 2020-03-18 | 2020-03-18 | 99 |  | Complete
100% | Vendor Compliance | 1d | 2020-03-17 | 2020-03-17 | 99FF |  | Complete
100% | Syndication | 14d | 2020-03-03 | 2020-03-20 |  |  | Complete
100% | Questionnaire Sent to Marketing | 1d | 2020-03-03 | 2020-03-03 | 56FS +1d |  | Complete
100% | Questionnaire Completed | 13d | 2020-03-04 | 2020-03-20 | 103 |  | Complete
100% | Answer Automation (Call Center) | 5d | 2019-10-17 | 2019-10-23 |  |  | Complete
100% | Questionnaire Sent to Operations | 1d | 2019-10-17 | 2019-10-17 |  |  | Complete
100% | Questionnaire Completed | 1d | 2019-10-23 | 2019-10-23 | 106FS +3d |  | Complete
100% | Luther Towers Completed | 1d | 2020-03-18 | 2020-03-18 | 98FF |  | Complete
100% | 700 SoHo (Retrofit Timetable) | 49d | 2020-04-01 | 2020-06-08 |  | Ade Ayeni | Complete
100% | Termination Letter Received by CA (Cease Work in OneSite 4/17/20) | 1d | 2020-04-17 | 2020-04-17 |  |  | Complete
100% | Accounting setup | 4d | 2020-04-17 | 2020-04-22 | 110SS |  | Complete
100% | Send Accounting RealPage Order Number for Site | 4d | 2020-04-17 | 2020-04-22 |  |  | Complete
100% | Set up RealPage Accounting/Spend Management | 1d | 2020-04-22 | 2020-04-22 | 112FF |  | Complete
100% | Leasing and Rents (Consulting & Standard Business Model) | 8d | 2020-04-20 | 2020-04-29 | 111SS |  | Complete
100% | Conversion/Go Live | 4d | 2020-04-20 | 2020-04-23 |  |  | Complete
100% | Onesite to Onesite Retrofit | 4d | 2020-04-20 | 2020-04-23 | 110 |  | Complete
100% | Post Migration | 4d | 2020-04-24 | 2020-04-29 |  |  | Complete
100% | Add Additional Fiscal Years in Onesite | 1d | 2020-04-24 | 2020-04-24 | 116 | Ade Ayeni | Complete
100% | Accounting Global Journal Settings | 1d | 2020-04-24 | 2020-04-24 | 116 | Ade Ayeni | Complete
100% | Confirm Delinquent/Prepaid Amounts Match Cut-off Date Data | 3d | 2020-04-27 | 2020-04-29 | 118 |  | Complete | Retrofit - All information copied over to our instance of OneSite
100% | Confirm Transactions Match Cut-off Date Data | 3d | 2020-04-27 | 2020-04-29 | 120SS |  | Complete | Retrofit - All information copied over to our instance of OneSite
100% | Begin Data Entry for Manual Data | 4d | 2020-04-24 | 2020-04-29 | 116 |  | Complete
100% | Resident Portal | 1d | 2020-04-23 | 2020-04-23 | 115FF |  | Complete
100% | Payments | 6d | 2020-04-21 | 2020-04-28 |  |  | Complete
100% | Information for Payments | 6d | 2020-04-21 | 2020-04-28 |  |  | Complete
100% | Retrieve Voided Check/Bank Letter Verification | 3d | 2020-04-21 | 2020-04-23 | 110FS +1d |  | Complete
100% | Retrieve Average Transaction Amount | 3d | 2020-04-21 | 2020-04-23 | 110FS +1d |  | Complete
100% | Retrieve Highest Rent Amount | 3d | 2020-04-21 | 2020-04-23 | 110FS +1d |  | Complete
100% | Retrieve W9 | 3d | 2020-04-21 | 2020-04-23 | 110FS +1d |  | Complete
100% | Send Documents/Information to Payments Consultant | 3d | 2020-04-24 | 2020-04-28 | 126, 127, 128, 129 |  | Complete
100% | Go Live | 1d | 2020-04-27 | 2020-04-27 | 115FS +1d |  | Complete
100% | Resident Direct | 1d | 2020-04-27 | 2020-04-27 | 115FS +1d |  | Complete
100% | Facilities | 1d | 2020-04-24 | 2020-04-24 | 116 |  | Complete
100% | Document Management (product) | 36d | 2020-04-20 | 2020-06-08 |  |  | Complete
100% | Blue Moon | 27d | 2020-04-20 | 2020-05-26 |  |  | Complete | Delayed obtaining Blue Moon credentials
100% | Obtain Blue Moon Credentials | 1d | 2020-04-20 | 2020-04-20 | 110 |  | Complete
100% | Update OneSite with Credentials | 15d | 2020-04-21 | 2020-05-11 | 136 | Ade Ayeni | Complete | Delayed - Orders Pending
100% | Confirm Blue Moon Connection | 1d | 2020-05-15 | 2020-05-15 | 137FS +3d |  | Complete
100% | Confirm Blue Moon Docs to be used | 1d | 2020-05-26 | 2020-05-26 | 138FS +6d |  | Complete
100% | Go Live | 9d | 2020-05-27 | 2020-06-08 |  |  | Complete
100% | Consulting for Blue Moon Packets | 9d | 2020-05-27 | 2020-06-08 |  |  | Complete
100% | Test Packet Ready for Review | 9d | 2020-05-27 | 2020-06-08 |  |  | Complete
100% | Discuss anything not populating or generating correctly on custom forms | 8d | 2020-05-27 | 2020-06-05 | 139 |  | Complete
100% | Update any Leasing & Rents changes and merge fields, if necessary | 8d | 2020-05-27 | 2020-06-05 | 143SS |  | Complete
100% | Review and Confirm Packet Content | 9d | 2020-05-27 | 2020-06-08 | 143SS |  | Complete
100% | Screening | 0 | 2020-04-24 | 2020-04-24 | 116FF +1d |  | Complete
100% | Online Leasing | 2d | 2020-04-29 | 2020-04-30 |  |  | Complete
100% | Online Leasing Goes Live | 1d | 2020-04-29 | 2020-04-29 | 116FF +4d |  | Complete
100% | Website Link Sent to Site Management to update current Website | 1d | 2020-04-29 | 2020-04-29 | 148FF | Ade Ayeni | Complete | "Apply Now" button in header linked
100% | Site Management Completion/Update | 1d | 2020-04-30 | 2020-04-30 | 149 |  | Complete
100% | eSupply GPO | 1d | 2020-04-24 | 2020-04-24 | 115 |  | Complete
100% | eProcurement | 3d | 2020-04-24 | 2020-04-28 |  |  | Complete
100% | Vendors Set up | 2d | 2020-04-24 | 2020-04-27 | 115 |  | Complete
100% | eProcurment completion | 1d | 2020-04-28 | 2020-04-28 | 153 |  | Complete
100% | Vendor Compliance | 1d | 2020-04-27 | 2020-04-27 | 153FF |  | Complete
100% | Syndication | 5d | 2020-04-01 | 2020-04-07 |  |  | Complete
100% | Questionnaire Sent to Marketing | 1d | 2020-04-01 | 2020-04-01 |  |  | Complete
100% | Questionnaire Completed | 1d | 2020-04-07 | 2020-04-07 | 157FS +3d |  | Complete
100% | Answer Automation (Call Center) | 22d | 2020-04-01 | 2020-04-30 |  |  | Complete
100% | Questionnaire Sent to Operations | 1d | 2020-04-01 | 2020-04-01 |  |  | Complete
100% | Questionnaire Completed | 1d | 2020-04-07 | 2020-04-07 | 160FS +3d |  | Complete
100% | Contact Center Activated | 1d | 2020-04-23 | 2020-04-23 | 161FS +11d |  | Complete
100% | Email Sent to Site Team for Setup | 1d | 2020-04-30 | 2020-04-30 | 162FS +4d |  | Complete | Delayed - Email Setup
100% | 700 Soho Completed | 0 |  |  |  |  | Complete
0% | Falcon Point | 19d | 2020-11-01 | 2020-11-25 |  | Ade Ayeni | Not Started | POST-PONED
0% | Termination Letter Received | 1d | 2020-11-01 | 2020-11-01
0% | Accounting setup | 4d | 2020-11-02 | 2020-11-05 | 166SS
0% | Send Accounting RealPage Order Number for Site | 4d | 2020-11-02 | 2020-11-05
0% | Set up RealPage Accounting/Spend Management | 1d | 2020-11-05 | 2020-11-05 | 168FF
0% | Syndication | 5d | 2020-11-02 | 2020-11-06
0% | SalesForce Case Sent to Marketing | 1d | 2020-11-02 | 2020-11-02 | 166SS
0% | Worksheet Completed | 3d | 2020-11-03 | 2020-11-05 | 171
0% | CIMPL Questionnaire Completed | 1d | 2020-11-06 | 2020-11-06 | 171FS +3d
0% | Answer Automation (Call Center) | 15d | 2020-11-02 | 2020-11-20
0% | SalesForce Case Sent to Marketing | 1d | 2020-11-02 | 2020-11-02 | 166SS
0% | Worksheet Completed | 1d | 2020-11-03 | 2020-11-03 | 171
0% | Contact Center Activated | 1d | 2020-11-19 | 2020-11-19 | 176FS +11d
0% | Email Sent to Site Team for Setup | 1d | 2020-11-20 | 2020-11-20 | 177 |  |  | Delayed - Email Setup
0% | Leasing and Rents (Consulting & Standard Business Model) | 16d | 2020-11-02 | 2020-11-23 | 167SS
0% | RealPage Sends Questionnaire and Leasing Details Workbooks | 1d | 2020-11-02 | 2020-11-02 | 166SS
0% | Confirm Site Cut-off Date for Conversion Data | 1d | 2020-11-02 | 2020-11-02
0% | Complete Questionnaire and Leasing Details Workbooks | 1d | 2020-11-05 | 2020-11-05 | 166FS +3d
0% | Send both Workbooks to Consultant | 1d | 2020-11-06 | 2020-11-06 | 182
0% | Conversion/Go Live | 8d | 2020-11-09 | 2020-11-18
0% | Migration | 8d | 2020-11-09 | 2020-11-18 | 183
0% | Post Migration | 12d | 2020-11-06 | 2020-11-23
0% | Add Additional Fiscal Years in OneSite | 1d | 2020-11-19 | 2020-11-19 | 185
0% | Confirm Delinquent/Prepaid Amounts Match Cut-off Date Data | 1d | 2020-11-19 | 2020-11-19 | 185
0% | Confirm Transactions Match Cut-off Date Data | 3d | 2020-11-19 | 2020-11-23 | 185
0% | Begin Data Entry for Manual Data | 1d | 2020-11-06 | 2020-11-06 | 183SS
0% | Resident Portal | 1d | 2020-11-20 | 2020-11-20 | 184FS +1d
0% | Payments | 12d | 2020-11-03 | 2020-11-18
0% | Information for Payments | 6d | 2020-11-03 | 2020-11-10
0% | Retrieve Voided Check/Bank Letter Verification | 3d | 2020-11-03 | 2020-11-05 | 166FS +1d
0% | Retrieve Average Transaction Amount | 3d | 2020-11-03 | 2020-11-05 | 166FS +1d
0% | Retrieve Highest Rent Amount | 3d | 2020-11-03 | 2020-11-05 | 166FS +1d
0% | Retrieve W9 | 3d | 2020-11-03 | 2020-11-05 | 166FS +1d
0% | Send Documents/Information to Payments Consultant | 3d | 2020-11-06 | 2020-11-10 | 194, 195, 196, 197
0% | Go Live | 1d | 2020-11-18 | 2020-11-18 | 184FF
0% | Resident Direct | 1d | 2020-11-20 | 2020-11-20 | 184FS +1d
0% | Facilities | 1d | 2020-11-19 | 2020-11-19 | 185
0% | Document Management (product) | 18d | 2020-11-02 | 2020-11-25
0% | Blue Moon | 10d | 2020-11-02 | 2020-11-13 |  |  |  | Delayed obtaining Blue Moon credentials
0% | Obtain Blue Moon Credentials | 1d | 2020-11-02 | 2020-11-02 | 166
0% | Update OneSite with Credentials | 2d | 2020-11-03 | 2020-11-04 | 204 |  |  | Delayed - Orders Pending
0% | Confirm Blue Moon Connection | 1d | 2020-11-09 | 2020-11-09 | 205FS +2d
0% | Confirm Blue Moon Docs to be used | 1d | 2020-11-13 | 2020-11-13 | 206FS +3d
0% | Go Live | 8d | 2020-11-16 | 2020-11-25
0% | Consulting for Blue Moon Packets | 8d | 2020-11-16 | 2020-11-25
0% | Test Packet Ready for Review | 8d | 2020-11-16 | 2020-11-25
0% | Discuss anything not populating or generating correctly on custom forms | 8d | 2020-11-16 | 2020-11-25 | 207
0% | Update any Leasing & Rents changes and merge fields, if necessary | 8d | 2020-11-16 | 2020-11-25 | 211SS
0% | Review and Confirm Packet Content | 8d | 2020-11-16 | 2020-11-25 | 211SS
0% | Screening | 0 | 2020-11-19 | 2020-11-19 | 185FF +1d
0% | Online Leasing | 1d | 2020-11-20 | 2020-11-20
0% | Online Leasing Goes Live | 1d | 2020-11-20 | 2020-11-20 | 185FF +2d
0% | Website Link Sent to Site Management to update current Website | 1d | 2020-11-20 | 2020-11-20 | 216FF | Ade Ayeni |  | "Apply Now" button in header linked
0% | Site Management Completion/Update | 1d | 2020-11-20 | 2020-11-20 | 217SS
0% | eSupply GPO | 1d | 2020-11-20 | 2020-11-20 | 184FS +1d
0% | eProcurement | 15d | 2020-11-02 | 2020-11-20
0% | Vendors Set up | 5d | 2020-11-02 | 2020-11-06 | 166
0% | eProcurment completion | 10d | 2020-11-09 | 2020-11-20 | 221
0% | Vendor Compliance | 1d | 2020-11-20 | 2020-11-20 | 222FF
0% | Falcon Point Completed | 0
0% | Thomas Park Lofts | 19d | 2020-11-01 | 2020-11-25 |  | Ade Ayeni | Not Started | POST-PONED
0% | Termination Letter Received | 1d | 2020-11-01 | 2020-11-01
0% | Accounting setup | 4d | 2020-11-02 | 2020-11-05 | 226SS
0% | Send Accounting RealPage Order Number for Site | 4d | 2020-11-02 | 2020-11-05
0% | Set up RealPage Accounting/Spend Management | 1d | 2020-11-05 | 2020-11-05 | 228FF
0% | Syndication | 5d | 2020-11-02 | 2020-11-06
0% | SalesForce Case Sent to Marketing | 1d | 2020-11-02 | 2020-11-02 | 226SS
0% | Worksheet Completed | 3d | 2020-11-03 | 2020-11-05 | 231
0% | CIMPL Questionnaire Completed | 1d | 2020-11-06 | 2020-11-06 | 231FS +3d
0% | Answer Automation (Call Center) | 15d | 2020-11-02 | 2020-11-20
0% | SalesForce Case Sent to Marketing | 1d | 2020-11-02 | 2020-11-02 | 226SS
0% | Worksheet Completed | 1d | 2020-11-03 | 2020-11-03 | 231
0% | Contact Center Activated | 1d | 2020-11-19 | 2020-11-19 | 236FS +11d
0% | Email Sent to Site Team for Setup | 1d | 2020-11-20 | 2020-11-20 | 237 |  |  | Delayed - Email Setup
0% | Leasing and Rents (Consulting & Standard Business Model) | 16d | 2020-11-02 | 2020-11-23 | 227SS
0% | RealPage Sends Questionnaire and Leasing Details Workbooks | 1d | 2020-11-02 | 2020-11-02 | 226SS
0% | Confirm Site Cut-off Date for Conversion Data | 1d | 2020-11-02 | 2020-11-02
0% | Complete Questionnaire and Leasing Details Workbooks | 1d | 2020-11-05 | 2020-11-05 | 226FS +3d
0% | Send both Workbooks to Consultant | 1d | 2020-11-06 | 2020-11-06 | 242
0% | Conversion/Go Live | 8d | 2020-11-09 | 2020-11-18
0% | Migration | 8d | 2020-11-09 | 2020-11-18 | 243
0% | Post Migration | 12d | 2020-11-06 | 2020-11-23
0% | Add Additional Fiscal Years in OneSite | 1d | 2020-11-19 | 2020-11-19 | 245
0% | Confirm Delinquent/Prepaid Amounts Match Cut-off Date Data | 1d | 2020-11-19 | 2020-11-19 | 245
0% | Confirm Transactions Match Cut-off Date Data | 3d | 2020-11-19 | 2020-11-23 | 245
0% | Begin Data Entry for Manual Data | 1d | 2020-11-06 | 2020-11-06 | 243SS
0% | Resident Portal | 1d | 2020-11-20 | 2020-11-20 | 244FS +1d
0% | Payments | 12d | 2020-11-03 | 2020-11-18
0% | Information for Payments | 6d | 2020-11-03 | 2020-11-10
0% | Retrieve Voided Check/Bank Letter Verification | 3d | 2020-11-03 | 2020-11-05 | 226FS +1d
0% | Retrieve Average Transaction Amount | 3d | 2020-11-03 | 2020-11-05 | 226FS +1d
0% | Retrieve Highest Rent Amount | 3d | 2020-11-03 | 2020-11-05 | 226FS +1d
0% | Retrieve W9 | 3d | 2020-11-03 | 2020-11-05 | 226FS +1d
0% | Send Documents/Information to Payments Consultant | 3d | 2020-11-06 | 2020-11-10 | 254, 255, 256, 257
0% | Go Live | 1d | 2020-11-18 | 2020-11-18 | 244FF
0% | Resident Direct | 1d | 2020-11-20 | 2020-11-20 | 244FS +1d
0% | Facilities | 1d | 2020-11-19 | 2020-11-19 | 245
0% | Document Management (product) | 18d | 2020-11-02 | 2020-11-25
0% | Blue Moon | 10d | 2020-11-02 | 2020-11-13 |  |  |  | Delayed obtaining Blue Moon credentials
0% | Obtain Blue Moon Credentials | 1d | 2020-11-02 | 2020-11-02 | 226
0% | Update OneSite with Credentials | 2d | 2020-11-03 | 2020-11-04 | 264 |  |  | Delayed - Orders Pending
0% | Confirm Blue Moon Connection | 1d | 2020-11-09 | 2020-11-09 | 265FS +2d
0% | Confirm Blue Moon Docs to be used | 1d | 2020-11-13 | 2020-11-13 | 266FS +3d
0% | Go Live | 8d | 2020-11-16 | 2020-11-25
0% | Consulting for Blue Moon Packets | 8d | 2020-11-16 | 2020-11-25
0% | Test Packet Ready for Review | 8d | 2020-11-16 | 2020-11-25
0% | Discuss anything not populating or generating correctly on custom forms | 8d | 2020-11-16 | 2020-11-25 | 267
0% | Update any Leasing & Rents changes and merge fields, if necessary | 8d | 2020-11-16 | 2020-11-25 | 271SS
0% | Review and Confirm Packet Content | 8d | 2020-11-16 | 2020-11-25 | 271SS
0% | Screening | 0 | 2020-11-19 | 2020-11-19 | 245FF +1d
0% | Online Leasing | 1d | 2020-11-20 | 2020-11-20
0% | Online Leasing Goes Live | 1d | 2020-11-20 | 2020-11-20 | 245FF +2d
0% | Website Link Sent to Site Management to update current Website | 1d | 2020-11-20 | 2020-11-20 | 276FF | Ade Ayeni |  | "Apply Now" button in header linked
0% | Site Management Completion/Update | 1d | 2020-11-20 | 2020-11-20 | 277SS
0% | eSupply GPO | 1d | 2020-11-20 | 2020-11-20 | 244FS +1d
0% | eProcurement | 15d | 2020-11-02 | 2020-11-20
0% | Vendors Set up | 5d | 2020-11-02 | 2020-11-06 | 226
0% | eProcurment completion | 10d | 2020-11-09 | 2020-11-20 | 281
0% | Vendor Compliance | 1d | 2020-11-20 | 2020-11-20 | 282FF
0% | Thomas Park Lofts Completed | 0
0% | Wolf Creek Condos | 19d | 2020-11-01 | 2020-11-25 |  | Ade Ayeni | Not Started | POST-PONED
0% | Termination Letter Received | 1d | 2020-11-01 | 2020-11-01
0% | Accounting setup | 4d | 2020-11-02 | 2020-11-05 | 286SS
0% | Send Accounting RealPage Order Number for Site | 4d | 2020-11-02 | 2020-11-05
0% | Set up RealPage Accounting/Spend Management | 1d | 2020-11-05 | 2020-11-05 | 288FF
0% | Syndication | 5d | 2020-11-02 | 2020-11-06
0% | SalesForce Case Sent to Marketing | 1d | 2020-11-02 | 2020-11-02 | 286SS
0% | Worksheet Completed | 3d | 2020-11-03 | 2020-11-05 | 291
0% | CIMPL Questionnaire Completed | 1d | 2020-11-06 | 2020-11-06 | 291FS +3d
0% | Answer Automation (Call Center) | 15d | 2020-11-02 | 2020-11-20
0% | SalesForce Case Sent to Marketing | 1d | 2020-11-02 | 2020-11-02 | 286SS
0% | Worksheet Completed | 1d | 2020-11-03 | 2020-11-03 | 291
0% | Contact Center Activated | 1d | 2020-11-19 | 2020-11-19 | 296FS +11d
0% | Email Sent to Site Team for Setup | 1d | 2020-11-20 | 2020-11-20 | 297 |  |  | Delayed - Email Setup
0% | Leasing and Rents (Consulting & Standard Business Model) | 16d | 2020-11-02 | 2020-11-23 | 287SS
0% | RealPage Sends Questionnaire and Leasing Details Workbooks | 1d | 2020-11-02 | 2020-11-02 | 286SS
0% | Confirm Site Cut-off Date for Conversion Data | 1d | 2020-11-02 | 2020-11-02
0% | Complete Questionnaire and Leasing Details Workbooks | 1d | 2020-11-05 | 2020-11-05 | 286FS +3d
0% | Send both Workbooks to Consultant | 1d | 2020-11-06 | 2020-11-06 | 302
0% | Conversion/Go Live | 8d | 2020-11-09 | 2020-11-18
0% | Migration | 8d | 2020-11-09 | 2020-11-18 | 303
0% | Post Migration | 12d | 2020-11-06 | 2020-11-23
0% | Add Additional Fiscal Years in OneSite | 1d | 2020-11-19 | 2020-11-19 | 305
0% | Confirm Delinquent/Prepaid Amounts Match Cut-off Date Data | 1d | 2020-11-19 | 2020-11-19 | 305
0% | Confirm Transactions Match Cut-off Date Data | 3d | 2020-11-19 | 2020-11-23 | 305
0% | Begin Data Entry for Manual Data | 1d | 2020-11-06 | 2020-11-06 | 303SS
0% | Resident Portal | 1d | 2020-11-20 | 2020-11-20 | 304FS +1d
0% | Payments | 12d | 2020-11-03 | 2020-11-18
0% | Information for Payments | 6d | 2020-11-03 | 2020-11-10
0% | Retrieve Voided Check/Bank Letter Verification | 3d | 2020-11-03 | 2020-11-05 | 286FS +1d
0% | Retrieve Average Transaction Amount | 3d | 2020-11-03 | 2020-11-05 | 286FS +1d
0% | Retrieve Highest Rent Amount | 3d | 2020-11-03 | 2020-11-05 | 286FS +1d
0% | Retrieve W9 | 3d | 2020-11-03 | 2020-11-05 | 286FS +1d
0% | Send Documents/Information to Payments Consultant | 3d | 2020-11-06 | 2020-11-10 | 314, 315, 316, 317
0% | Go Live | 1d | 2020-11-18 | 2020-11-18 | 304FF
0% | Resident Direct | 1d | 2020-11-20 | 2020-11-20 | 304FS +1d
0% | Facilities | 1d | 2020-11-19 | 2020-11-19 | 305
0% | Document Management (product) | 18d | 2020-11-02 | 2020-11-25
0% | Blue Moon | 10d | 2020-11-02 | 2020-11-13 |  |  |  | Delayed obtaining Blue Moon credentials
0% | Obtain Blue Moon Credentials | 1d | 2020-11-02 | 2020-11-02 | 286
0% | Update OneSite with Credentials | 2d | 2020-11-03 | 2020-11-04 | 324 |  |  | Delayed - Orders Pending
0% | Confirm Blue Moon Connection | 1d | 2020-11-09 | 2020-11-09 | 325FS +2d
0% | Confirm Blue Moon Docs to be used | 1d | 2020-11-13 | 2020-11-13 | 326FS +3d
0% | Go Live | 8d | 2020-11-16 | 2020-11-25
0% | Consulting for Blue Moon Packets | 8d | 2020-11-16 | 2020-11-25
0% | Test Packet Ready for Review | 8d | 2020-11-16 | 2020-11-25
0% | Discuss anything not populating or generating correctly on custom forms | 8d | 2020-11-16 | 2020-11-25 | 327
0% | Update any Leasing & Rents changes and merge fields, if necessary | 8d | 2020-11-16 | 2020-11-25 | 331SS
0% | Review and Confirm Packet Content | 8d | 2020-11-16 | 2020-11-25 | 331SS
0% | Screening | 0 | 2020-11-19 | 2020-11-19 | 305FF +1d
0% | Online Leasing | 1d | 2020-11-20 | 2020-11-20
0% | Online Leasing Goes Live | 1d | 2020-11-20 | 2020-11-20 | 305FF +2d
0% | Website Link Sent to Site Management to update current Website | 1d | 2020-11-20 | 2020-11-20 | 336FF | Ade Ayeni |  | "Apply Now" button in header linked
0% | Site Management Completion/Update | 1d | 2020-11-20 | 2020-11-20 | 337SS
0% | eSupply GPO | 1d | 2020-11-20 | 2020-11-20 | 304FS +1d
0% | eProcurement | 15d | 2020-11-02 | 2020-11-20
0% | Vendors Set up | 5d | 2020-11-02 | 2020-11-06 | 286
0% | eProcurment completion | 10d | 2020-11-09 | 2020-11-20 | 341
0% | Vendor Compliance | 1d | 2020-11-20 | 2020-11-20 | 342FF
Wolf Creek Condos Completed
77% | Genesis Kent (WhiteHall Terrace, Summit Hill, Hickory Mills) | 46d | 2020-12-22 | 2021-02-23 |  | Ade Ayeni | In Progress
100% | Cut-Off | 1d | 2020-12-22 | 2020-12-22
100% | Accounting setup | 4d | 2020-12-22 | 2020-12-25 | 346SS
100% | Send Accounting RealPage Order Number for Site | 4d | 2020-12-22 | 2020-12-25
100% | Set up RealPage Accounting/Spend Management | 1d | 2020-12-25 | 2020-12-25 | 348FF
100% | Syndication | 5d | 2021-01-21 | 2021-01-27
100% | Implementation Worksheet Sent to RM and CM | 1d | 2021-01-21 | 2021-01-21 | 346SS +22d
100% | Worksheet Completed | 3d | 2021-01-22 | 2021-01-26 | 351
100% | Send to RealPage Engagement Manager | 1d | 2021-01-27 | 2021-01-27 | 351FS +3d
100% | Answer Automation (Call Center) | 21d | 2021-01-21 | 2021-02-18
100% | Implementation Worksheet Sent to RM and CM | 1d | 2021-01-21 | 2021-01-21 | 346SS +22d
100% | Worksheet Completed | 3d | 2021-01-22 | 2021-01-26 | 351
0% | Contact Center Activated | 5d | 2021-02-11 | 2021-02-17 | 356FS +11d
0% | Email Sent to Site Team for Setup | 1d | 2021-02-18 | 2021-02-18 | 357
66% | Leasing and Rents (Consulting & Standard Business Model) | 16d | 2020-12-22 | 2021-01-12 | 347SS
100% | RealPage Sends Questionnaire and Leasing Details Workbooks | 1d | 2020-12-22 | 2020-12-22 | 346SS
100% | Confirm Site Cut-off Date for Conversion Data | 1d | 2020-12-22 | 2020-12-22 |  |  |  | 12/4/2020
100% | Complete Questionnaire and Leasing Details Workbooks | 1d | 2020-12-24 | 2020-12-24 | 346FS +1d
100% | Send both Workbooks to Consultant | 0 | 2020-12-24 | 2020-12-24 | 362
100% | Conversion/Go Live | 10d | 2020-12-25 | 2021-01-07
100% | Migration | 10d | 2020-12-25 | 2021-01-07 | 363
33% | Post Migration | 13d | 2020-12-24 | 2021-01-12 |  |  |  | Heavily delayed due to not having complete information during DD
100% | Add Additional Fiscal Years in OneSite | 1d | 2021-01-08 | 2021-01-08 | 365 | Ade Ayeni |  | Heavily delayed due to not having complete information during DD
0% | Confirm Delinquent/Prepaid Amounts Match Cut-off Date Data | 1d | 2021-01-08 | 2021-01-08 | 365 |  |  | Heavily delayed due to not having complete information during DD
0% | Confirm Transactions Match Cut-off Date Data | 3d | 2021-01-08 | 2021-01-12 | 365 |  |  | Heavily delayed due to not having complete information during DD
100% | Begin Data Entry for Manual Data | 1d | 2020-12-24 | 2020-12-25 | 363SS |  |  | Heavily delayed due to not having complete information during DD
100% | Resident Portal | 1d | 2021-01-11 | 2021-01-11 | 364FS +1d
100% | Payments | 24d | 2020-12-24 | 2021-01-26
100% | Information for Payments | 24d | 2020-12-24 | 2021-01-26
100% | Retrieve Voided Check/Bank Letter Verification | 3d | 2020-12-24 | 2020-12-28 | 346FS +1d
100% | Retrieve Average Transaction Amount | 24d | 2020-12-24 | 2021-01-26 | 346FS +1d
100% | Retrieve Highest Rent Amount | 24d | 2020-12-24 | 2021-01-26 | 346FS +1d
100% | Retrieve W9 | 3d | 2020-12-24 | 2020-12-28 | 346FS +1d
100% | Send Documents/Information to Payments Consultant | 0 | 2021-01-26 | 2021-01-26 | 374, 375, 376, 377
100% | Go Live | 1d | 2021-01-07 | 2021-01-07 | 364FF
100% | Resident Direct | 0 | 2021-01-08 | 2021-01-08 | 364FS +1d
100% | Facilities | 1d | 2021-01-08 | 2021-01-08 | 365
94% | Document Management (product) | 45d | 2020-12-23 | 2021-02-23
100% | Blue Moon | 37d | 2020-12-23 | 2021-02-11 |  |  |  | Delayed obtaining Blue Moon credentials
100% | Obtain Blue Moon Credentials | 28d | 2020-12-23 | 2021-01-29 | 346
100% | Update OneSite with Credentials | 2d | 2021-02-01 | 2021-02-02 | 384 |  |  | Delayed - Orders Pending
100% | Confirm Blue Moon Connection | 1d | 2021-02-05 | 2021-02-05 | 385FS +2d
100% | Confirm Blue Moon Docs to be used | 1d | 2021-02-11 | 2021-02-11 | 386FS +3d
67% | Go Live | 8d | 2021-02-12 | 2021-02-23
67% | Consulting for Blue Moon Packets | 8d | 2021-02-12 | 2021-02-23
67% | Test Packet Ready for Review | 8d | 2021-02-12 | 2021-02-23
100% | Discuss anything not populating or generating correctly on custom forms | 8d | 2021-02-12 | 2021-02-23 | 387
100% | Update any Leasing & Rents changes and merge fields, if necessary | 8d | 2021-02-12 | 2021-02-23 | 391SS
0% | Review and Confirm Packet Content | 8d | 2021-02-12 | 2021-02-23 | 391SS
100% | Screening | 0 | 2021-01-08 | 2021-01-08 | 365FF +1d
100% | Online Leasing | 1d | 2021-01-11 | 2021-01-11
100% | Online Leasing Goes Live | 1d | 2021-01-11 | 2021-01-11 | 365FF +2d
100% | Website Link Sent to Site Management to update current Website | 1d | 2021-01-11 | 2021-01-11 | 396FF | Ade Ayeni |  | "Apply Now" button in header linked
100% | Site Management Completion/Update | 1d | 2021-01-11 | 2021-01-11 | 397SS
100% | eSupply GPO | 1d | 2021-01-11 | 2021-01-11 | 364FS +1d
32% | eProcurement | 15d | 2020-12-23 | 2021-01-12
95% | Vendors Set up | 5d | 2020-12-23 | 2020-12-29 | 346
0% | eProcurment completion | 10d | 2020-12-30 | 2021-01-12 | 401
95% | Vendor Compliance | 1d | 2021-01-12 | 2021-01-12 | 402FF
Genesis Kent Portfolio Completed
| 1501 Herman (Ground Up) | 25d | 2020-10-01 | 2020-11-04 |  | Ade Ayeni | Not Started | POST-PONED
| Asset Closed | 1d | 2020-10-01 | 2020-10-01
| Accounting setup | 5d | 2020-10-01 | 2020-10-07 | 406SS
| Send Accounting RealPage Order Number for Site | 4d | 2020-10-01 | 2020-10-06
| Set up RealPage Accounting | 1d | 2020-10-07 | 2020-10-07 | 408
| Leasing and Rents (Consulting & Standard Business Model) | 25d | 2020-10-01 | 2020-11-04 | 407SS
| RealPage Sends Questionnaire and Leasing Details Workbooks | 1d | 2020-10-01 | 2020-10-01 | 407SS
| Confirm Site Cut-off Date for Conversion Data | 1d | 2020-10-01 | 2020-10-01 | 407SS
| Complete Questionnaire and Leasing Details Workbooks | 5d | 2020-10-02 | 2020-10-08 | 406, 412
| Send both Workbooks to Consultant | 0 | 2020-10-15 | 2020-10-15 | 413FS +5d | Ade Ayeni
| Conversion/Go Live | 8d | 2020-10-16 | 2020-10-27
| Migration | 8d | 2020-10-16 | 2020-10-27 | 414
| Post Migration | 6d | 2020-10-28 | 2020-11-04
| Add Additional Fiscal Years in Onesite | 1d | 2020-10-28 | 2020-10-28 | 416 | Ade Ayeni
| Confirm Delinquent/Prepaid Amounts Match Cut-off Date Data | 3d | 2020-10-29 | 2020-11-02 | 418
| Confirm Transactions Match Cut-off Date Data | 3d | 2020-10-29 | 2020-11-02 | 419SS
| Begin Data Entry for Manual Data | 6d | 2020-10-28 | 2020-11-04 | 412, 416
| Resident Portal | 1d | 2020-10-15 | 2020-10-15 | 415SF
| Payments | 18d | 2020-10-05 | 2020-10-28
| Information for Payments | 18d | 2020-10-05 | 2020-10-28
| Retrieve Voided Check/Bank Letter Verification | 3d | 2020-10-05 | 2020-10-07 | 406FS +1d
| Retrieve Average Transaction Amount | 3d | 2020-10-05 | 2020-10-07 | 406FS +1d
| Retrieve Highest Rent Amount | 3d | 2020-10-05 | 2020-10-07 | 406FS +1d
| Retrieve W9 | 3d | 2020-10-05 | 2020-10-07 | 406FS +1d
| Send Documents/Information to Payments Consultant | 3d | 2020-10-08 | 2020-10-12 | 425, 426, 427, 428
| Go Live | 0 | 2020-10-28 | 2020-10-28 | 415FS +1d
| Resident Direct | 0 | 2020-10-28 | 2020-10-28 | 415FS +1d
| Facilities | 1d | 2020-10-28 | 2020-10-28 | 416
| Purchasing | 2d | 2020-10-29 | 2020-10-30
| Accurate Purchasing Workflow Received | 1d | 2020-10-29 | 2020-10-29 | 416FS +1d
| Set up Purchasing Workflow | 1d | 2020-10-30 | 2020-10-30 | 434 | Ade Ayeni
| Document Management (product) | 21d | 2020-10-02 | 2020-10-30
| RealPage Sends Custom Packet Workbook | 1d | 2020-10-02 | 2020-10-02 | 406
| Complete Custom Packets Workbook | 4d | 2020-10-05 | 2020-10-08 | 437
| Send Workbook to Consultant | 1d | 2020-10-09 | 2020-10-09 | 438 | Ade Ayeni
| Go Live | 3d | 2020-10-28 | 2020-10-30 | 415
| Consulting for Custom Packets | 3d | 2020-10-28 | 2020-10-30
| Test Packet Ready for Review (Meeting) | 3d | 2020-10-28 | 2020-10-30
| Discuss anything not populating or generating correctly on custom forms | 3d | 2020-10-28 | 2020-10-30 | 439
| Update any Leasing & Rents changes and merge fields, if necessary | 1d | 2020-10-30 | 2020-10-30 | 443FF
| Confirm Packet Content | 1d | 2020-10-30 | 2020-10-30 | 443FF
| Schedule Custom Packet Process Overview (Call) | 1d | 2020-10-30 | 2020-10-30 | 443FF
| Screening | 1d | 2020-10-28 | 2020-10-28 | 416FF +1d
| Online Leasing | 3d | 2020-10-28 | 2020-10-30
| Online Leasing Goes Live | 1d | 2020-10-28 | 2020-10-28 | 416FF +1d
| Website Link Sent to Site Management to update current Website | 1d | 2020-10-28 | 2020-10-28 | 449FF | Ade Ayeni
| Site Management Completion/Update | 2d | 2020-10-29 | 2020-10-30 | 450
| eSupply GPO | 1d | 2020-10-28 | 2020-10-28 | 415
| eProcurement | 6d | 2020-10-28 | 2020-11-04
| Vendors Set up | 5d | 2020-10-28 | 2020-11-03 | 415
| eProcurment completion | 1d | 2020-11-04 | 2020-11-04 | 454
| Vendor Compliance | 1d | 2020-11-03 | 2020-11-03 | 454FF
| Syndication | 14d | 2020-10-05 | 2020-10-22 | 406FS +1d
| 1501 Herman Completed | 1d | 2020-11-04 | 2020-11-04 | 453FF